Project team:

· Nokulunga Dlamini (202303388)

· Nontokozo Nhlengetfwa (202302216)

· Siphosethu Mhlanga (202301480)

· Lungiswa Ndlangamandla (202304348)

Project Plan: Student Task Management System

1. Introduction

This project involves the design and development of a Student Task Management System to help students organize, track, and manage academic tasks including assignments, projects, and examinations. The system addresses poor organization, missed deadlines, and academic stress.

Summary: A simple, accessible, web-based task management tool tailored for students.

2. User/Client Involvement

· Users: University students who need to manage academic tasks.

· Client/Instructor: Will provide approval on requirements and evaluate final delivery.

· Student involvement: At least 5 students will be consulted during requirements gathering and user testing. They will provide feedback on usability, feature set, and interface design.

· Schedule for user input:

· Week 1: Requirements interviews

· Week 4: Prototype testing

· Week 6: Final user acceptance testing

3. Risks

| Risks | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Team members have limited web development experience | medium | High | Allocate first week for self-learning (HTML/CSS/JS, Flask/Django) |
| scope creep(adding too many features) | Medium | Medium | Define clear MVP features: task creation, deadlines, simple reminders |
| Incomplete testing due to time constraints | Medium | Medium | Prioritize testing core features (add, edit, delete tasks |
| Poor user adoption if interface is not intuitive | Low | High | Conduct early usability tests with 3–5 students and iterate |

4. Standards, Guidelines and Procedures

· Coding standards: Use meaningful variable names, consistent indentation (2 or 4 spaces), and inline comments for complex logic.

· Documentation: Maintain a shared Google Doc for meeting notes and decisions.

· Version control: Use Git with meaningful commit messages. All changes must be committed to the shared GitHub repository.

· Communication: Weekly sync meetings every Monday at 4 PM via WhatsApp or in person. Daily status updates on Trello.

5. Organization of the Project

Relation to other projects: This is a standalone academic project with no dependencies on other concurrent projects.

Project organization:

· Project Manager (Nokulunga Dlamini): Coordinates tasks, deadlines, and team communication.

· Analyst/Designer (Lungiswa Ndlangamandla): Gathers requirements, creates wireframes, designs database schema.

· Programmers (Nontokozo Nhlengetfwa & Siphosethu Mhlanga): Implement front-end and back-end functionality.

· Tester (All members): Each member tests different features; Nontokozo leads test planning.

Training requirements:

· HTML/CSS/JavaScript basics (2 days for those less familiar)

· Flask/Django or Node.js tutorial (3 days)

· Git basics (1 day)

· Schedule: All training to be completed by end of Week 1.

6. Project Phases

Life cycle model: Agile (Scrum) with 1-week sprints.

Phase Tasks Milestone Deliverable Effort (person-days)

| Phase | Tasks | Milestone | Deliverables | Effort(person-days) |
| --- | --- | --- | --- | --- |
| 1.Requirements | User interviews,define features | Requirements specifications on approved documents | Requirements docs | 3 |
| 2.Design | Wireframes, database schema, user flow | Design review completed | UI mockups, ER diagram | 4 |
| 3.Implementation (Sprint 1) | Task creation,Task listing | Basic functionality working | prototype | 6 |
| 4.Implementation (sprint 2) | Deadlines, edits, delete tasks | Feature complete | Beta version | 6 |
| 5.Implementation ( Sprint 3) | Reminders(simple), user login | All core features done | final system | 4 |
| 6. Testing | Unit tests,integration tests, user testing | Test pass rate >90% | Test reports | 3 |
| 7. Deployment and Documentation | local deployment, user manual | final demo ready | GitHub repo+ demo | 2 |

Critical path: Design → Implementation Sprint 1 → Implementation Sprint 2 → Testing → Deployment.

Total estimated effort: 27 person-days over 6 weeks.

7. Requirements Analysis and Design

Methods:

· User interviews with 5 students (semi-structured questions about current task management habits).

· Use case diagrams to identify key interactions (create task, view tasks, set deadline, receive reminder).

· Task flow analysis to map user journeys.

Techniques:

· Persona creation (e.g., “Busy Thabo – engineering student with 5 courses”).

· Paper prototyping early in design phase.

Tools:

· Draw.io for use case and ER diagrams.

· Figma (free tier) for UI mockups.

· Google Forms for collecting user feedback.

Expected outputs: Requirements specification document, wireframes, database schema (tables: Users, Tasks, Categories/optional).

8. Implementation

Resources and tools:

· Front-end: HTML5, CSS3, JavaScript (vanilla or React if time permits).

· Back-end: Python with Flask (simpler) or Django.

· Database: SQLite (development) or PostgreSQL (if deployed).

· IDE: VS Code for all team members.

· Version control: Git and GitHub (private repository).

· Hosting (optional): Localhost for demo; PythonAnywhere for basic cloud deployment.

Implementation approach: Build iteratively – start with task creation and listing, then add deadlines, then edit/delete, then reminders and user accounts.

9. Testing

Test environment:

· Local development server on each team member’s laptop.

· Browsers: Chrome (primary), Firefox (secondary).

· Mobile view via browser DevTools.

Test equipment: Personal laptops (minimum 2) and at least one smartphone for responsive testing.

Integration order:

1. Test task creation module alone.

2. Integrate and test task listing.

3. Add and test edit/delete functionality.

4. Add deadlines and test sorting/filtering.

5. Add reminders and user login, test end-to-end.

Testing procedures:

· Unit tests: Each function (e.g., add_task(), delete_task()) tested with valid and invalid inputs.

· Integration tests: Combine two modules at a time (e.g., create + list).

· User acceptance testing: 3–5 students perform typical tasks (add 3 tasks, mark one complete, edit a deadline) while being observed. Record any confusion or errors.

Pass criteria: 90% of planned test cases pass; no critical bugs.

10. Resources

Human resources: 4 team members (roles defined in section 5).

Software resources (all free/open source):

· VS Code (code editor)

· Git / GitHub (version control)

· Figma (design)

· Draw.io (diagrams)

· Trello (task tracking)

· Google Drive / Docs (documentation)

· Flask or Django (back-end)

· SQLite or PostgreSQL (database)

· Chrome DevTools (debugging)

Hardware resources:

· Personal laptops (4 units)

· Smartphones for testing (at least 2)

· Internet access for collaboration and research

Facilities: University library or computer lab for team meetings.

11. Monitoring and Control Mechanisms

· Task board: Trello with columns: To Do, In Progress, Review, Done. Updated daily.

· Weekly sprint planning: Every Monday, assign tasks for the week.

· Daily standup: Quick 10-minute WhatsApp voice note or text update each morning.

· Burndown chart: Track remaining effort vs. time (simple Google Sheet).

· Milestone reviews: At the end of each phase (see section 6), team checks if deliverables meet criteria.

· Risk review: Discuss risks every Wednesday; update mitigation as needed.

12. Quality Assurance

· Code reviews: Every pull request reviewed by at least one other team member before merging.

· Test coverage: Core features (create, read, update, delete tasks) must have 100% unit test coverage.

· Usability standard: A new user should be able to add a task within 30 seconds without instructions.

· Performance standard: Task list loads within 2 seconds for up to 100 tasks.

· Documentation review: User manual checked for clarity by a student who did not participate in development.

13. Documentation and Delivery

Documentation to be produced:

· Requirements specification

· Design document (wireframes, database schema, use cases)

· User manual (simple one-page guide with screenshots)

· Developer guide (setup instructions, file structure, API if any)

· Test report (test cases, results, and bug fixes)

· Final project report (summarizing process, challenges, and outcomes)

Delivery format:

· GitHub repository containing all source code and documentation.

· A working demo (either localhost or basic cloud deployment on PythonAnywhere/Replit).

· A 5-minute video walkthrough demonstrating all features.

· A printed or PDF copy of the final report submitted to the instructor